## UPS Schedule
Ironwood Point Data Center — Building A, Phase 1
UPS System Procurement & Installation Schedule ¦ Project No. MDC-2026-0417 ¦ Updated 07/04/2026
Task ID | Task | Start Date | End Date | Duration (days) | Status | Notes
1.0 | UPS Specification Issued for Construction | 2026-05-04 | 2026-05-04 | 1 | Complete | Section 26 33 53 Rev. 2 issued
2.0 | Vendor Submittal — Product Data & Shop Drawings | 2026-06-10 | 2026-06-25 | 16 | Complete | Submittal 26 33 53-01 received from Apex Critical Power
3.0 | Engineer Submittal Review | 2026-06-26 | 2026-07-17 | 22 | In Progress | RFI-016 (autonomy) and RFI-017 (efficiency) open pending resolution
3.1 | Resolve Battery Autonomy Discrepancy (RFI-016) | 2026-06-27 | 2026-07-10 | 14 | Open | Contractor to confirm 15-min compliant string or submit deviation request
3.2 | Resolve Efficiency Discrepancy (RFI-017) | 2026-06-27 | 2026-07-10 | 14 | Open | Coordinate with Mechanical re: UPS room heat rejection impact
4.0 | Submittal Resubmission (if required) | 2026-07-11 | 2026-07-24 | 14 | Not Started | Contingent on RFI-016 / RFI-017 resolution
5.0 | Purchase Order Release | 2026-07-25 | 2026-07-25 | 1 | Not Started | 20-24 week factory lead time from this date
6.0 | Factory Witness Test (FWT) | 2026-11-30 | 2026-12-04 | 5 | Not Started | Owner's Rep and Commissioning Agent to witness
7.0 | Equipment Delivery to Site | 2026-12-15 | 2026-12-18 | 4 | Not Started | Coordinate crane pick and rigging with GC
8.0 | UPS & Battery Cabinet Installation | 2027-01-05 | 2027-01-23 | 19 | Not Started | Includes seismic anchoring and grounding
9.0 | Manufacturer Startup | 2027-01-26 | 2027-01-28 | 3 | Not Started | Factory-authorized technician required
10.0 | Integrated Systems Test (IST) | 2027-02-08 | 2027-02-12 | 5 | Not Started | Full-load bank test, battery discharge, ATS transfer scenarios
11.0 | Owner Training | 2027-02-15 | 2027-02-16 | 2 | Not Started | Minimum 8 hours O&M training
12.0 | Substantial Completion — UPS System | 2027-02-19 | 2027-02-19 | 1 | Not Started | Milestone per master project schedule